## Risk Assessment
FInding | Tool | Threat Type (S/T/R/I/D/E) | MITTRE ATT&CK Technique | NIST CSF Function | ISO 27001 Control | Potential Impact | Impact Score (1-5) | Likelihood (1-5) | Risk Score | T | Owner | Status (Open/Closed) | Target Date
MFA is not enabled for root account | Prowler | E - Elevation of Privilege | T1078.004 | PR.AA-05 | A.5.17 | Increasing the risk of unauthorized access if credentials are compromised | 5 | 4 | 20 | Enable MFA where possible | TBD | Open | 2025-10-01
No CloudTrail trails enabled with logging were found | Prowler | R - Repudiation | T1562.002 | DE.CM-03 PR.PS-04 | A.8.15 | Absence of CloudTrail logging disables tracking of account activities, making it harder to detect suspicious behavior | 4 | 3 | 12 | Enable multi-region CloudTrail with S3 logging | TBD | Open | 2025-10-01
Root user in the account was last accessed 0 days ago | Prowler | E - Elevation of Privilege | T1098.001 | PR.DS-01 PR.DS-02 PR.DS-10 PR.DS-11 | A.8.2 | Recent root user activity suggests potential misuse or lack of least privilege enforcement | 2 | 1 | 2 | Implement recent checking mechanism on all accounts | TBD | Open | 2025-10-01
Block Public Access is not configured for the account | Prowler | I - Information Disclosure | T1133 | PR.IR-01 | A.5.15 | No blockage for public access exposes the whole system to severe threats from public | 5 | 3 | 15 | Enable Block Public Access for the account and buckets | TBD | Open | 2025-10-01
IAM password policy does not require at least one lowercase letter | Prowler | S - Spoofing | T1110.002 | PR.AA-05 | A.5.17 | No password policy increases the likelihood of weak passwords being used | 3 | 3 | 9 | Update IAM password policy to require lowercase, uppercase, numbers, and symbol | TBD | Open | 2025-10-01
Password expiration is not set | Prowler | S - Spoofing | T1003.005 | PR.AA-05 | A.5.17 | Lack of password expiration allows outdated credentials to remain active | 4 | 3 | 12 | Establish a password expiration policies | TBD | Open | 2025-10-01
User cli-security-audit does not have any type of MFA enabled | Prowler | E - Elevation of Privilege | T1110.002 | PR.AA-05 | A.5.17 | Users performing CLI or security audits without MFA are vulnerable to credential theft | 4 | 3 | 12 | Enable MFA for cli-security-audit | TBD | Open | 2025-10-01
User cli-security-audit has long lived credentials with access to other services than IAM or STS | Prowler | E - Elevation of Privilege I - Information Disclosure | T1552.006 | PR.AA-05 | A.5.15 | Persistent credentials for services beyond IAM or STS pose a security risk if exposed | 4 | 3 | 12 | Replace long-lived keys with IAM roles and temporary credentials | TBD | Open | 2025-10-01
Security group was created using the EC2 Launch Wizard | Prowler | T - Tampering D - Denial of Service | T1068 | PR.AA-01 | A.8.20 | Auto-generated security groups may have overly permissive rules, exposing resources | 3 | 2 | 6 | Restrict security group rules to necessary ports/protocols | TBD | Open | 2025-10-01
SSL Certificate Cannot Be Trusted | Nessus | S - Spoofing I - Information Disclosure | T1040 | PR.AA-04 | A.8.24 | Untrusted certificates could lead to man-in-the-middle attacks or data interception | 5 | 5 | 25 | Replace untrusted certificate with a valid one | TBD | Open | 2025-10-01

## FAIR Analysis
LEF = TEF x V
Total Loss = Primary Loss + Secondary Loss
ALE = LM x LEF
|  | Initial Threat Impact | [14 empty] | Without Mitigation
Finding |  | Threat Event Frequency (TEF - events/yr) |  | Vulnerability Rating (V) |  | Loss Event Frequency (LEF - events/yr) |  | Loss Magnitude (LM - Euros) | [5 empty] | Anualized Loss Expectancy (ALE) |  | Risk Grade | Finding | Anualized Loss Expectancy (ALE) |  | Risk Grade
|  | Min | Max | Min | Max | Min | Max | Primary Loss (Euros) |  | Secondary Loss (Euros) |  | Total Loss (Euros)
[8 empty] | Min | Max | Min | Max | Min | Max | Min | Max |  |  | Min | Max
MFA is not enabled for root account |  | 100 | 1000 | 90% | 100% | 90 | 1000 | 9200 | 920000 | 46000 | 4600000 | 55200 | 5520000 | 4968000 | 5520000000 | Medium | MFA is not enabled for root account | 4968000 | 5520000000 | Medium
No CloudTrail trails enabled with logging were found |  | 10 | 100 | 80% | 90% | 8 | 90 | 46000 | 4600000 | 10000 | 1000000 | 56000 | 5600000 | 448000 | 504000000 | Low | No CloudTrail trails enabled with logging were found | 448000 | 504000000 | Low
Root user in the account was last accessed 0 days ago |  | 100 | 1000 | 80% | 90% | 80 | 900 | 46000 | 4600000 | 46000 | 4600000 | 92000 | 9200000 | 7360000 | 8280000000 | High | Root user in the account was last accessed 0 days ago | 7360000 | 8280000000 | High
Block Public Access is not configured for the account |  | 1000 | 10000 | 50% | 80% | 500 | 8000 | 9200 | 1840000 | 46000 | 4600000 | 55200 | 6440000 | 27600000 | 51520000000 | Critical | Block Public Access is not configured for the account | 27600000 | 51520000000 | Critical
IAM password policy does not require at least one lowercase letter |  | 120 | 1200 | 30% | 50% | 36 | 600 | 9200 | 460000 | 9200 | 460000 | 18400 | 920000 | 662400 | 552000000 | Low | IAM password policy does not require at least one lowercase letter | 662400 | 552000000 | Low
Password expiration is not set |  | 120 | 1200 | 40% | 60% | 48 | 720 | 9200 | 460000 | 9200 | 460000 | 18400 | 920000 | 883200 | 662400000 | Low | Password expiration is not set | 883200 | 662400000 | Low
User cli-security-audit does not have any type of MFA enabled |  | 100 | 1000 | 90% | 100% | 90 | 1000 | 46000 | 1840000 | 9200 | 920000 | 55200 | 2760000 | 4968000 | 2760000000 | Medium | User cli-security-audit does not have any type of MFA enabled | 4968000 | 2760000000 | Medium
User cli-security-audit has long lived credentials with access to other services than IAM or STS |  | 100 | 1000 | 80% | 90% | 80 | 900 | 46000 | 4600000 | 46000 | 4600000 | 92000 | 9200000 | 7360000 | 8280000000 | High | User cli-security-audit has long lived credentials with access to other services than IAM or STS | 7360000 | 8280000000 | High
Security group was created using the EC2 Launch Wizard |  | 1000 | 10000 | 50% | 80% | 500 | 8000 | 9200 | 1840000 | 9200 | 920000 | 18400 | 2760000 | 9200000 | 22080000000 | High | Security group was created using the EC2 Launch Wizard | 9200000 | 22080000000 | High
SSL Certificate Cannot Be Trusted |  | 120 | 1200 | 30% | 50% | 36 | 600 | 9200 | 920000 | 9200 | 920000 | 18400 | 1840000 | 662400 | 1104000000 | Low | SSL Certificate Cannot Be Trusted | 662400 | 1104000000 | Low
With Mitigation
|  | Mitigation Impact | [14 empty] | Finding | Anualized Loss Expectancy (ALE) |  | Risk Grade
Recommended Mitigations | Expected Cost | Threat Event Frequency (TEF - events/yr) |  | Vulnerability Rating (V) |  | Loss Event Frequency (LEF - events/yr) |  | Loss Magnitude (LM - Euros) | [5 empty] | Anualized Loss Expectancy (ALE) |  | Risk Grade
|  | Min | Max | Min | Max | Min | Max | Primary Loss (Euros) |  | Secondary Loss (Euros) |  | Total Loss (Euros) | [5 empty] | Min | Max
[8 empty] | Min | Max | Min | Max | Min | Max | Min | Max |  | MFA is not enabled for root account | 552000 | 828000000 | Low
Enable MFA where possible | 1000 | 100 | 1000 | 10% | 15% | 10 | 150 | 9200 | 920000 | 46000 | 4600000 | 55200 | 5520000 | 552000 | 828000000 | Low | No CloudTrail trails enabled with logging were found | 5600 | 16800000 | Low
Enable multi-region CloudTrail with S3 logging | 1000 | 10 | 100 | 1% | 3% | 0.1 | 3 | 46000 | 4600000 | 10000 | 1000000 | 56000 | 5600000 | 5600 | 16800000 | Low | Root user in the account was last accessed 0 days ago | 460000 | 920000000 | Low
Implement recent checking mechanism on all accounts | 1000 | 100 | 1000 | 5% | 10% | 5 | 100 | 46000 | 4600000 | 46000 | 4600000 | 92000 | 9200000 | 460000 | 920000000 | Low | Block Public Access is not configured for the account | 2760000 | 4508000000 | Medium
Enable Block Public Access for the account and buckets | 2000 | 1000 | 10000 | 5% | 7% | 50 | 700 | 9200 | 1840000 | 46000 | 4600000 | 55200 | 6440000 | 2760000 | 4508000000 | Medium | IAM password policy does not require at least one lowercase letter | 22080 | 33120000 | Low
Update IAM password policy to require lowercase, uppercase, numbers, and symbol | 500 | 120 | 1200 | 1% | 3% | 1.2 | 36 | 9200 | 460000 | 9200 | 460000 | 18400 | 920000 | 22080 | 33120000 | Low | Password expiration is not set | 110400 | 88320000 | Low
Establish a password expiration policies | 500 | 120 | 1200 | 5% | 8% | 6 | 96 | 9200 | 460000 | 9200 | 460000 | 18400 | 920000 | 110400 | 88320000 | Low | User cli-security-audit does not have any type of MFA enabled | 552000 | 414000000 | Low
Enable MFA for cli-security-audit | 0 | 100 | 1000 | 10% | 15% | 10 | 150 | 46000 | 1840000 | 9200 | 920000 | 55200 | 2760000 | 552000 | 414000000 | Low | User cli-security-audit has long lived credentials with access to other services than IAM or STS | 920000 | 1380000000 | Low
Replace long-lived keys with IAM roles and temporary credentials | 500 | 100 | 1000 | 10% | 15% | 10 | 150 | 46000 | 4600000 | 46000 | 4600000 | 92000 | 9200000 | 920000 | 1380000000 | Low | Security group was created using the EC2 Launch Wizard | 920000 | 2760000000 | Low
Restrict security group rules to necessary ports/protocols | 500 | 1000 | 10000 | 5% | 10% | 50 | 1000 | 9200 | 1840000 | 9200 | 920000 | 18400 | 2760000 | 920000 | 2760000000 | Low | SSL Certificate Cannot Be Trusted | 220800 | 331200000 | Low
Replace untrusted certificate with a valid one | 500 | 120 | 1200 | 10% | 15% | 12 | 180 | 9200 | 920000 | 9200 | 920000 | 18400 | 1840000 | 220800 | 331200000 | Low
Financial Impact
Anualized Loss Expectancy Saved (ALE)
[14 empty] | Min | Max
[14 empty] | 4415000 | 4691999900
[14 empty] | 441400 | 487199990
[14 empty] | 6899000 | 7359999900
[14 empty] | 24838000 | 47011999000
[14 empty] | 639820 | 518879880
[14 empty] | 772300 | 574079880
[14 empty] | 4416000 | 2345999900
[14 empty] | 6439500 | 6899999900
[14 empty] | 8279500 | 19319999000
[14 empty] | 441100 | 772799880
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: IBM 2024 reports average breach cost of $4.45M (€4.09M). AWS-specific breaches (e.g., crypto mining) range from $10K to $1M+. Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $500K × 0.92, max: $1M × 0.92).
Note on J10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: IBM 2024 reports average breach cost of $4.45M (€4.09M). AWS-specific breaches (e.g., crypto mining) range from $10K to $1M+. Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $500K × 0.92, max: $1M × 0.92).
Note on K10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to $20M (€18.4M), reputational damage ($50K–$5M, €46K–€4.6M), legal costs ($10K–$500K, €9.2K–€460K). Estimate (EUR): €46K–€4.6M
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to $20M (€18.4M), reputational damage ($50K–$5M, €46K–€4.6M), legal costs ($10K–$500K, €9.2K–€460K). Estimate (EUR): €46K–€4.6M
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Delayed detection increases breach costs by 20–50% (IBM 2024). Costs include data loss, cleanup ($50K–$500K). Estimate (EUR): €46K–€460K (min: $50K × 0.92, most likely: $200K × 0.92 = €184K, max: $500K × 0.92).
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Delayed detection increases breach costs by 20–50% (IBM 2024). Costs include data loss, cleanup ($50K–$500K). Estimate (EUR): €46K–€460K (min: $50K × 0.92, most likely: $200K × 0.92 = €184K, max: $500K × 0.92).
Note on K11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Non-compliance fines (e.g., SOC 2, $10K–$1M), reputational damage ($10K–$500K). Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92).
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Non-compliance fines (e.g., SOC 2, $10K–$1M), reputational damage ($10K–$500K). Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92).
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage (e.g., EC2, S3, RDS misuse). Costs range from $50K to $5M. Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage (e.g., EC2, S3, RDS misuse). Costs range from $50K to $5M. Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Regulatory fines (e.g., GDPR, $20K–$5M), reputational damage ($50K–$2M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Regulatory fines (e.g., GDPR, $20K–$5M), reputational damage ($50K–$2M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: S3 breaches cost $10K–$2M (e.g., data theft, cleanup; IBM 2024 average breach cost €4.09M). Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: S3 breaches cost $10K–$2M (e.g., data theft, cleanup; IBM 2024 average breach cost €4.09M). Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to €20M, reputational damage ($50K–$5M, €46K–€4.6M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to €20M, reputational damage ($50K–$5M, €46K–€4.6M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Account compromise costs $10K–$500K (cleanup, data loss; IBM 2024). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Account compromise costs $10K–$500K (cleanup, data loss; IBM 2024). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on K14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on L14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Similar to weak password policy, $10K–$500K. Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on J15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Similar to weak password policy, $10K–$500K. Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on K15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on L15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on I16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: CLI user compromise costs $50K–$2M (e.g., service misuse; IBM 2024). Estimate (EUR): €46K–€1.84M (min: $50K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: CLI user compromise costs $50K–$2M (e.g., service misuse; IBM 2024). Estimate (EUR): €46K–€1.84M (min: $50K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage ($50K–$5M; IBM 2024) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on J17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage ($50K–$5M; IBM 2024) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines, reputational damage ($50K–$5M) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines, reputational damage ($50K–$5M) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: EC2 compromise costs $10K–$2M (e.g., ransomware, data theft; IBM 2024) Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: EC2 compromise costs $10K–$2M (e.g., ransomware, data theft; IBM 2024) Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Disruption, data interception costs $10K–$1M (IBM 2024) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on J19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Disruption, data interception costs $10K–$1M (IBM 2024) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on K19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Customer churn, reputational damage ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Customer churn, reputational damage ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on I28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: IBM 2024 reports average breach cost of $4.45M (€4.09M). AWS-specific breaches (e.g., crypto mining) range from $10K to $1M+. Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $500K × 0.92, max: $1M × 0.92).
Note on J28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: IBM 2024 reports average breach cost of $4.45M (€4.09M). AWS-specific breaches (e.g., crypto mining) range from $10K to $1M+. Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $500K × 0.92, max: $1M × 0.92).
Note on K28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to $20M (€18.4M), reputational damage ($50K–$5M, €46K–€4.6M), legal costs ($10K–$500K, €9.2K–€460K). Estimate (EUR): €46K–€4.6M
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to $20M (€18.4M), reputational damage ($50K–$5M, €46K–€4.6M), legal costs ($10K–$500K, €9.2K–€460K). Estimate (EUR): €46K–€4.6M
Note on I29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Delayed detection increases breach costs by 20–50% (IBM 2024). Costs include data loss, cleanup ($50K–$500K). Estimate (EUR): €46K–€460K (min: $50K × 0.92, most likely: $200K × 0.92 = €184K, max: $500K × 0.92).
Note on J29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Delayed detection increases breach costs by 20–50% (IBM 2024). Costs include data loss, cleanup ($50K–$500K). Estimate (EUR): €46K–€460K (min: $50K × 0.92, most likely: $200K × 0.92 = €184K, max: $500K × 0.92).
Note on K29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Non-compliance fines (e.g., SOC 2, $10K–$1M), reputational damage ($10K–$500K). Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92).
Note on L29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Non-compliance fines (e.g., SOC 2, $10K–$1M), reputational damage ($10K–$500K). Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92).
Note on I30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage (e.g., EC2, S3, RDS misuse). Costs range from $50K to $5M. Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on J30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage (e.g., EC2, S3, RDS misuse). Costs range from $50K to $5M. Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on K30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Regulatory fines (e.g., GDPR, $20K–$5M), reputational damage ($50K–$2M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Regulatory fines (e.g., GDPR, $20K–$5M), reputational damage ($50K–$2M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: S3 breaches cost $10K–$2M (e.g., data theft, cleanup; IBM 2024 average breach cost €4.09M). Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: S3 breaches cost $10K–$2M (e.g., data theft, cleanup; IBM 2024 average breach cost €4.09M). Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to €20M, reputational damage ($50K–$5M, €46K–€4.6M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines up to €20M, reputational damage ($50K–$5M, €46K–€4.6M). Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Account compromise costs $10K–$500K (cleanup, data loss; IBM 2024). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on J32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Account compromise costs $10K–$500K (cleanup, data loss; IBM 2024). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on K32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on L32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Similar to weak password policy, $10K–$500K. Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on J33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Similar to weak password policy, $10K–$500K. Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on K33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on L33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance issues ($10K–$500K). Estimate (EUR): €9.2K–€460K (min: $10K × 0.92, most likely: $100K × 0.92 = €92K, max: $500K × 0.92)
Note on I34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: CLI user compromise costs $50K–$2M (e.g., service misuse; IBM 2024). Estimate (EUR): €46K–€1.84M (min: $50K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: CLI user compromise costs $50K–$2M (e.g., service misuse; IBM 2024). Estimate (EUR): €46K–€1.84M (min: $50K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on I35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage ($50K–$5M; IBM 2024) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on J35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Broad access increases damage ($50K–$5M; IBM 2024) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on K35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines, reputational damage ($50K–$5M) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on L35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: GDPR fines, reputational damage ($50K–$5M) Estimate (EUR): €46K–€4.6M (min: $50K × 0.92, most likely: $1M × 0.92 = €920K, max: $5M × 0.92)
Note on I36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: EC2 compromise costs $10K–$2M (e.g., ransomware, data theft; IBM 2024) Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on J36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: EC2 compromise costs $10K–$2M (e.g., ransomware, data theft; IBM 2024) Estimate (EUR): €9.2K–€1.84M (min: $10K × 0.92, most likely: $500K × 0.92 = €460K, max: $2M × 0.92)
Note on K36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Reputational damage, compliance fines ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Disruption, data interception costs $10K–$1M (IBM 2024) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on J37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Disruption, data interception costs $10K–$1M (IBM 2024) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on K37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Customer churn, reputational damage ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)
Note on L37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data: Customer churn, reputational damage ($10K–$1M) Estimate (EUR): €9.2K–€920K (min: $10K × 0.92, most likely: $300K × 0.92 = €276K, max: $1M × 0.92)